## AMuRate
Activity | Task | Subtask | Subtask description | Status | Estimation | Release
Look up music | Search via songname | Enter text in song input field |  | Todo |  | TODO
Look up music | Search via artistname | Enter text in artist field |  | Todo |  | TODO
Look up music | Search via artist and songname | Enter text in both fields |  | Todo |  | TODO
Look up music | Inform user about request status | Display loading gif |  | Todo |  | TODO
View search results | List found songs | Display no songs found |  | Todo |  | TODO
View search results | List found artists | Display empty list when no artists found |  | Todo |  | TODO
View details | View song details | Link to the artist |  | Todo |  | TODO
View details | View song details | Link to YouTube |  | Todo |  | TODO
View details | View song details | Link to the album |  | Todo |  | TODO
View details | View artist details | List information about the artist |  | Todo |  | TODO
View details | View artist details | List most popular albums |  | Todo |  | TODO
View details | View artist details | List most popular tracks |  | Todo |  | TODO
View details | View album details | List tracks of album |  | Todo |  | TODO
View details | View album details | Link to artist of album |  | Todo |  | TODO
Manage history | Save history in DB | Save search history |  | Todo |  | TODO
Manage history | Save history in DB | Save viewed tracks |  | Todo |  | TODO
Manage history | Save history in DB | Save given ratings |  | Todo |  | TODO
Manage history | Display query results | List search history |  | Todo |  | TODO
Manage history | Display query results | List viewed tracks |  | Todo |  | TODO
Manage history | Display query results | List given ratings |  | Todo |  | TODO
Back end | Create remote database | Find host server |  | Todo |  | TODO
Back end | Create remote database | Create tables |  | Todo |  | TODO
Back end | Query remote DB | Retrieve average rating for a song |  | Todo |  | TODO
Back end | Query remote DB | Get amount of ratings given |  | Todo |  | TODO
Back end | Query remote DB | Protect from SQL-injections |  | Todo |  | TODO
Back end | Store given rating | Send rating to DB |  | Todo |  | TODO
Back end | Store given rating | Update frontend |  | Todo |  | TODO
Back end | Get information from Last.FM | Retrieve information via requests and key |  | Todo |  | TODO
Back end | Synchronize databases | Check connectivity |  | Todo |  | TODO
Back end | Synchronize databases | Send data to external database |  | Todo |  | TODO
Change Settings | Show settings | Show current and available languages |  | Todo |  | TODO
Change Settings | Change settings | Change language |  | Todo |  | TODO
Instructions | Provide instructions | Show information about how to use the app |  | Todo |  | TODO
Instructions | Provide instructions | Show a message when the user tries to do something wrong |  | Todo |  | TODO
Note on A2: details